## Sheet2
Item Code | Description | Start Date | End Date | Days to Complete | Responsible Party
1/23/1.1 | water leak | 2019-01-23 | 2019-01-23 | 1 | GC
1/23/1.2 | cafeteria demo | 2019-01-23 | 2019-01-23 | 1 | GC
1/23/1.3 | elevator | 2019-01-23 | 2019-02-11 | 19 | O
1/23/2.1 | bids due | 2019-01-23 | 2019-02-11 | 19 | GC
1/23/2.2 | Bulletin #1 | 2019-01-23 | 2019-01-23 | 1 | GC
1/23/2.3 | post bid meeting schedule | 2019-01-23 | 2019-02-13 | 21 | GC
1/23/4.1 | fire alarm | 2019-01-23 | 2019-03-06 | 42 | D
1/23/4.2 | lighting controls | 2019-01-23 | 2019-03-05 | 41 | D
1/23/5.1 | 3 bid RFI's | 2019-01-23 | 2019-02-11 | 19 | D
1/23/6.1 | addendum #1 | 2019-01-23 | 2019-01-24 | 1 | GC
1/23/6.2 | Bulletin #1 | 2019-01-23 | 2019-01-24 | 1 | GC
1/23/6.3 | Bulletin #2 | 2019-01-23 | 2019-03-27 | 63 | GC
1/23/7.1 | Unifier | 2019-01-23 | 2019-01-25 | 2 | GC/O
1/23/7.1a | Unifier | 2019-01-23 | 2019-01-24 | 1 | GC
1/23/7.1b | Unifier | 2019-01-23 | 2019-01-24 | 1 | O
1/23/7.2 | Plan grid training | 2019-01-23 | 2019-01-24 | 1 | GC
1/23/7.3 | PBA admin for plan grid | 2019-01-23 | 2019-01-24 | 1 | D
1/23/7.4 | project schedule concern | 2019-01-23 | 2019-01-24 | 1 | O
2/11/1.4 | kitchen abatement | 2019-02-11 | 2019-02-12 | 1 | GC
2/11/1.5 | Incident Report - fence collapse | 2019-02-11 | 2019-03-13 | 30 | GC
2/11/1.6 | basement demo/abatment | 2019-02-11 | 2019-03-27 | 44 | GC/O
2/11/1.6a | basement demo/abatment | 2019-02-11 | 2019-03-13 | 30 | GC
2/11/1.6b | basement demo/abatment | 2019-02-11 | 2019-02-25 | 14 | O
2/11/1.7 | Quarry tile | 2019-02-11 | 2019-03-20 | 37 | GC/D
2/11/1.7a | Quarry tile | 2019-02-11 | 2019-03-20 | 37 | GC
2/11/1.7b | Quarry tile | 2019-02-11 | 2019-02-25 | 14 | D
2/11/4.3 | TMP to issue Bulletin #2 | 2019-02-11 | 2019-02-28 | 17 | D
2/11/7.5 | furniture budget | 2019-02-11 | 2019-02-12 | 1 | O
2/11/7.6 | student room flooring | 2019-02-11 | 2019-03-06 | 23 | O
2/11/7.7 | KIVA flooring | 2019-02-11 | 2019-03-13 | 30 | O
2/11/7.8 | MSU leadership presentation | 2019-02-11 | 2019-02-12 | 1 | D
2/11/9.1 | install standpipes in dorm wign | 2019-02-11 | 2019-02-12 | 1 | GC
2/11/9.2 | student suite mock up | 2019-02-11 | 2019-02-12 | 1 | GC
2/11/9.3 | potentially ahead of schedule | 2019-02-11 | 2019-02-12 | 1 | GC
2/20/1.8 | glazed block demo | 2019-02-20 | 2019-03-06 | 14 | D
2/20/1.9 | fire suppression core | 2019-02-20 | 2019-03-04 | 12 | GC
2/20/1.10 | pipe insulation demo request | 2019-02-20 | 2019-03-06 | 14 | O
2/20/2.4 | award recommendations | 2019-02-20 | 2019-02-28 | 8 | GC/O
2/20/2.4a | award recommendations | 2019-02-20 | 2019-02-24 | 4 | GC
2/20/2.4b | award recommendations | 2019-02-20 | 2019-02-24 | 4 | O
2/20/2.5 | steel/drywall/fire suppression/plumbing approval | 2019-02-20 | 2019-02-21 | 1 | O
2/20/8.1 | completion schedule | 2019-02-20 | 2019-03-06 | 14 | GC
2/20/8.2 | 2 week look ahead | 2019-02-20 | 2019-03-27 | 35 | GC
2/20/3.1 | GC cost summary review | 2019-02-20 | 2019-03-06 | 14 | O
2/20/5.2 | acoustical baffles | 2019-02-20 | 2019-03-06 | 14 | GC
2/20/10.1 | plans submitted to fire/Safety office | 2019-02-20 | 2019-03-13 | 21 | GC
2/20/10.2 | electrician needs permit | 2019-02-20 | 2019-02-27 | 7 | GC
2/20/7.9 | Campus art locations | 2019-02-20 | 2019-03-27 | 35 | O
2/27/1.11 | 2nd floor demo | 2019-02-27 | 2019-03-06 | 7 | GC
2/27/1.12 | bay loading concerns | 2019-02-27 | 2019-03-06 | 7 | ALL
2/17/1.13 | abatment training | 2019-02-27 | 2019-03-06 | 7 | GC/O
2/27/1.13a | abatment training | 2019-02-27 | 2019-02-27 |  | O
2/21/1.13b | abatment training | 2019-02-27 | 2019-02-27 |  | GC
2/27/2.6 | budget update | 2019-02-27 | 2019-03-05 | 6 | O
2/27/2.7 | hot water piping approval | 2019-02-27 | 2019-03-05 | 6 | O
2/27/8.3 | fire suppression mock up | 2019-02-27 | 2019-03-13 | 14 | GC
2/27/8.4 | gypcrete | 2019-02-27 | 2019-03-06 | 7 | GC
2/27/8.5 | dorm flooring abatement | 2019-02-27 | 2019-03-06 | 7 | GC
2/27/4.4 | floor loading on 2nd floor | 2019-02-27 | 2019-02-28 | 1 | D
2/27/11.1 | pro-press substitute | 2019-02-27 | 2019-03-06 | 7 | GC
2/27/11.2 | master submittal log | 2019-02-27 | 2019-03-20 | 21 | ALL
2/27/7.10 | AV bid | 2019-02-27 | 2019-03-13 | 14 | ALL
2/27/7.11 | ADA budget | 2019-02-27 | 2019-03-27 | 28 | ALL
2/27/7.11a | ADA budget | 2019-02-27 | 2019-03-15 | 16 | GC
2/27/7.11b | ADA budget | 2019-02-27 | 2019-03-09 | 10 | D
2/27/7.11c | ADA budget | 2019-02-27 | 2019-02-28 | 1 | O
3/6/3.2 | price added angle iron for roof | 2019-03-06 | 2019-03-27 | 21 | ALL
3/6/12.1 | demo & additional work | 2019-03-06 | 2019-03-07 | 1 | D
3/6/5.3 | 6th floor - ceiling asbestos | 2019-03-06 | 2019-03-07 | 1 | GC
3/13/2.8 | Kiva Lighting | 2019-03-13 | 2019-03-14 | 1 | O
3/13/2.9 | Englarged glass area | 2019-03-13 | 2019-03-14 | 1 | O
3/13/2.10 | Alt #3 VE idea | 2019-03-13 | 2019-03-27 | 14 | ALL
3/13/2.10a | Alt #3 VE idea | 2019-03-13 | 2019-03-26 | 13 | GC
3/13/2.10b | Alt #3 VE idea | 2019-03-13 | 2019-03-19 | 6 | O
3/13/2.10c | Alt #3 VE idea | 2019-03-13 | 2019-03-19 | 6 | D
3/13/3.3 | hot water piping replacement | 2019-03-13 | 2019-03-14 | 1 | O
3/13/3.4 | Bulletin #2 pricing | 2019-03-13 | 2019-03-20 | 7 | O
3/13/3.5 | Replaced damaged light | 2019-03-13 | 2019-03-20 | 7 | GC
3/13/4.5 | CAD drawings | 2019-03-13 | 2019-03-14 | 1 | D
3/13/4.6 | 2nd floor metal framing | 2019-03-13 | 2019-03-14 | 1 | D
3/13/4.7 | sprinkler head cages | 2019-03-13 | 2019-03-14 | 1 | GC
3/13/4.8 | FADE | 2019-03-13 | 2019-03-27 | 14 | ALL
3/13/4.8a | FADE | 2019-03-13 | 2019-03-26 | 13 | D
3/13/4.8b | FADE | 2019-03-13 | 2019-03-14 | 1 | O
3/13/4.8c | FADE | 2019-03-13 | 2019-03-14 | 1 | GC
3/13/4.9 | AV design | 2019-03-13 | 2019-03-14 | 1 | D
3/13/5.4 | cold formed metal framing | 2019-03-13 | 2019-03-14 | 1 | D
3/13/11.3 | shop questions/review | 2019-03-13 | 2019-03-27 | 14 | D
3/13/7.12 | fire alarm knocked out | 2019-03-13 | 2019-03-14 | 1 | D
3/13/7.13 | KIVA lighting | 2019-03-13 | 2019-03-27 | 14 | GC/D
3/13/7.14 | WIFI | 2019-03-13 | 2019-03-27 | 14 | O/D
3/13/13.1 | items currently purchased | 2019-03-13 | 2019-03-20 | 7 | GC
3/13/13.2 | items to be included in scope | 2019-03-13 | 2019-03-20 | 7 | ?
3/13/13.3 | Generate bid package | 2019-03-13 | 2019-03-27 | 14 | O
3/13/13.4 | Dates | 2019-03-13 | 2019-03-27 | 14 | O
3/20/1.14 | asbestos awareness | 2019-03-20 | 2019-03-21 | 1 | GC
3/20/8.6 | wall layout | 2019-03-20 | 2019-03-21 | 1 | D
3/20/4.10 | cold form metal framing - box beam | 2019-03-20 | 2019-03-21 | 1 | D
3/20/5.6 | #76 compactor room ceiling demo | 2019-03-20 | 2019-03-27 | 7 | O
3/20/5.7 | #57 classroom ceiling height @ bulkhead | 2019-03-20 | 2019-03-27 | 7 | D
3/20/10.3 | H&R has permit | 2019-03-20 | 2019-03-21 | 1 | GC
3/20/7.15 | fire alarm demo | 2019-03-20 | 2019-03-21 | 1 | O/D
3/20/7.15a | fire alarm demo | 2019-03-20 | 2019-03-20 |  | D
3/20/7.15b | fire alarm demo | 2019-03-20 | 2019-03-20 |  | O
3/20/7.16 | furniture meeting | 2019-03-20 | 2019-03-27 | 7 | D
3/27/1.15 | subs must wear PPE | 2019-03-27 | 2019-03-28 | 1 | GC
3/27/1.16 | additional basement samples | 2019-03-27 | 2019-03-28 | 1 | ALL
3/27/8.7 | basement shop demo | 2019-03-27 | 2019-03-28 | 1 | GC
3/27/8.8 | low density fill - 2nd floor | 2019-03-27 | 2019-04-09 | 13 | GC
3/27/3.6 | existing basement conduit support | 2019-03-27 | 2019-03-28 | 1 | GC
3/27/5.8 | digital screen mounts | 2019-03-27 | 2019-03-28 | 1 | ALL
3/27/11.4 | MEP | 2019-03-27 | 2019-03-28 | 1 | D
3/27/6.4 | ASI #1 | 2019-03-27 | 2019-03-28 | 1 | ALL
3/27/7.17 | no work during final exams | 2019-03-27 | 2019-03-28 | 1 | GC
3/27/7.18 | Art on Campus Meeting | 2019-03-27 | 2019-04-10 | 14 | O
4/3/8.9 | Existing gas line turned off | 2019-04-03 | 2019-04-16 | 13 | O
4/3/4.11 | 1st floor ceiling duct penetration | 2019-04-03 | 2019-04-04 | 1 | D
4/3/4.12 | TMP to provide specific floor box location | 2019-04-03 | 2019-04-04 | 1 | D
4/3/4.13 | TMP to provide saw cut layout | 2019-04-03 | 2019-04-04 | 1 | D
4/3/5.9 | RFI #95 access to install plumbing | 2019-04-03 | 2019-04-04 | 1 | GC
4/3/11.5 | Future submittals go to Matt P to forward to TMP | 2019-04-03 | 2019-04-17 | 14 | O
4/3/11.6 | Guy (MSU) to review light fixture submittal | 2019-04-03 | 2019-04-04 | 1 | ALL
4/3/6.5 | Bulletin #3 issued | 2019-04-03 | 2019-04-17 | 14 | GC
4/3/7.19 | Expoxy floor color finalize hold up | 2019-04-03 | 2019-04-17 | 14 | D
4/3/7.20 | request to demo existing fire suppression system to second floor pipe penetrations | 2019-04-03 | 2019-04-10 | 7 | GC
4/3/7.21 | requested access to dorm area for core layout | 2019-04-03 | 2019-04-10 | 7 | GC
4/10/8.10 | wall taken down new pump room first floor | 2019-04-10 | 2019-04-24 | 14 | ALL
4/10/8.11 | steel delivery coordination, road closure | 2019-04-10 | 2019-04-24 | 14 | GC/O
4/10/3.7 | Ball valves approved | 2019-04-10 | 2019-04-11 | 1 | GC
4/10/3.8 | existing abandoned gas pipe basement removed | 2019-04-10 | 2019-04-11 | 1 | GC
4/10/5.10 | #96,97,98,99,101 steel RFI expedite | 2019-04-10 | 2019-04-11 | 1 | D
4/10/5.11 | RFI #93 | 2019-04-10 | 2019-04-17 | 7 | D |  | 2 week look ahead
4/10/6.6 | Bulletin #4 | 2019-04-10 | 2019-04-17 | 7 | GC |  | #76 compactor room ceiling demo
4/10/6.7 | Bulletin #5, cable tray elec floor box | 2019-04-10 | 2019-04-11 | 1 | GC |  | #57 classroom ceiling height @ bulkhead
4/10/7.22 | Additional ceiling removal room 41 | 2019-04-10 | 2019-04-11 | 1 | GC |  | 1st floor ceiling duct penetration
4/10/7.23 | Existing fin tube | 2019-04-10 | 2019-04-17 | 7 | ALL |  | #96,97,98,99,101 steel RFI expedite
4/10/7.24 | how many IGDs included fire system | 2019-04-10 | 2019-04-11 | 1 | GC |  | #11 steel
4/17/8.12 | Steam shutdown | 2019-04-17 | 2019-04-18 | 1 | O |  | 215 Air Line Locations
4/17/8.13 | All dorm rooms unlocked 5:00AM | 2019-04-17 | 2019-04-18 | 1 | GC |  | 223 Door HW for existing
4/17/8.14 | Master campus schedule for summer | 2019-04-17 | 2019-04-30 | 13 | O |  | 064023 Interior Architectural
4/17/8.15 | Finals week classroom schedule | 2019-04-17 | 2019-04-18 | 1 | GC |  | 225 LPC Height
4/17/3.9 | Basement fire suppression piping above ceiling | 2019-04-17 | 2019-04-18 | 1 | GC |  | 227 Steel Railing
4/17/7.25 | A6.2 & A12.2 furniture plan | 2019-04-17 | 2019-04-18 | 1 | D |  | 096519 Resilient Tile Flooring
4/17/7.26 | no external content placed on IGDs | 2019-04-17 | 2019-04-18 | 1 | GC |  | 227 Rockford to send steel information
4/17/7.27 | ADA ramp letter to MSU legal | 2019-04-17 | 2019-04-18 | 1 | ALL |  | 229 Screen heigh - TMP to return
4/17/7.28 | TMP alternate guardrail for rooftop HVAC | 2019-04-17 | 2019-05-01 | 14 | ALL |  | 115213 Projection Screen
4/17/7.29 | Write up and budget convert C202C computer lab | 2019-04-17 | 2019-04-30 | 13 | GC/D |  | 230 Paint first floor storage
4/24/2.11 | A/V, Epoxy floor, overhead doors | 2019-04-24 | 2019-04-25 | 1 | GC |  | 231 Mechanical Room MEP Removal
4/24/2.11a | A/V, Epoxy floor, overhead doors | 2019-04-24 | 2019-04-25 | 1 |  |  | 232 Projector screen size
4/24/8.16 | first room fire alarm conduit mockup | 2019-04-24 | 2019-04-25 | 1 | GC |  | 115213-1 Projection Screens
4/24/8.17 | hot water shutoff 6:00AM | 2019-04-24 | 2019-04-25 | 1 | GC |  | 064023-3 Millwork Shop Drawings
4/24/3.10 | review cost summary log | 2019-04-24 | 2019-05-08 | 14 | GC |  | 102800-1 Bathroom Accessories
4/24/6.8 | Bulletin #6 | 2019-04-24 | 2019-04-25 | 1 | GC |  | 234 Access panel size
4/24/7.30 | Need access to rooms 11,26,28 | 2019-04-24 | 2019-05-08 | 14 | O |  | 236 Control Panel Placement
4/24/7.31 | Room C211A IT changes, ceiling, light, paint, walls | 2019-04-24 | 2019-05-08 | 14 | D |  | 237 Sink Removal
4/24/7.32 | Cable tray spec | 2019-04-24 | 2019-05-01 | 7 | D |  | 055213 - Railings
4/24/7.33 | Piping penetration sleeves | 2019-04-24 | 2019-05-01 | 7 | D |  | 230923 - DDC HVAC Controls
4/24/7.34 | Water shutoff notice | 2019-04-24 | 2019-05-08 | 14 | GC |  | 233713 Grills Registers Diffusers
5/08/8.18 | MSU remove furniture piano projectors KIVA | 2019-05-08 | 2019-05-22 | 14 | O |  | 093000 Tiling product data
5/08/4.14 | Painting fire alarm fire suppression risers | 2019-05-08 | 2019-05-09 | 1 | GC |  | 1st Floor Ceiling Grid
5/08/5.12 | RFI #119 | 2019-05-08 | 2019-05-09 | 1 | O |  | 064023 Millwork Shop Drawings
5/08/11.7 | LaForce Total Door and LCN closers | 2019-05-08 | 2019-05-09 | 1 | GC
5/08/6.9 | Bulletin #7 | 2019-05-08 | 2019-05-15 | 7 | GC
5/08/7.35 | Crane swing concern, plan to set crane, tree damage waiver | 2019-05-08 | 2019-05-15 | 7 | GC/O
5/15/1.17 | review safety and freq of GC safety inspection | 2019-05-15 | 2019-05-16 | 1 | GC
5/15/1.18 | upload GC and trade site safety program, tool box talk, safety report | 2019-05-15 | 2019-05-16 | 1 | GC
5/15/8.19 | 6th floor fire suppression shop drawings | 2019-05-15 | 2019-05-23 | 8 | D
5/15/10.4 | pricing for supporting existing basement conduit | 2019-05-15 | 2019-05-17 | 2 | GC/D
5/15/7.36 | Floor variance C211, C213, C215 | 2019-05-15 | 2019-05-17 | 2 | ALL
5/15/7.37 | when water will be turned back on | 2019-05-15 | 2019-05-29 | 14 | GC
5/15/7.38 | elevator room abatement | 2019-05-15 | 2019-05-29 | 14 | GC/O
5/15/7.39 | review fire alarm conduit layout in South lobby | 2019-05-15 | 2019-05-17 | 2 | ALL
5/15/7.40 | potential change to penthouse access | 2019-05-15 | 2019-05-17 | 2 | O
5/22/1.19 | South dorm wing coring concrete beam | 2019-05-22 | 2019-05-24 | 2 | O/D
5/22/5.13 | RFI requesting to lower D hallway ceiling | 2019-05-22 | 2019-05-24 | 2 | GC
5/22/6.10 | Bulletin to capture AV changes | 2019-05-22 | 2019-06-06 | 15 | ALL
5/22/7.41 | Review fire panel location lobbies | 2019-05-22 | 2019-06-18 | 27 | O/D
5/22/7.42 | Water shutoff entire building duration | 2019-05-22 | 2019-06-05 | 14 | GC
5/22/7.43 | Wonder bodies equipment removed | 2019-05-22 | 2019-05-24 | 2 | O
5/22/7.44 | Central core south stair ceiling removed steel install | 2019-05-22 | 2019-05-24 | 2 | ALL
5/22/7.45 | Two approved roofers backed out | 2019-05-22 | 2019-05-24 | 2 | ALL
5/29/8.20 | Steel Shop and RFI roof curb | 2019-05-29 | 2019-06-13 | 15 | D
5/29/4.15 | Fire panel locations | 2019-05-29 | 2019-06-13 | 15 | ALL
5/29/4.16 | Intermediate offices | 2019-05-29 | 2019-06-13 | 15 | ALL
5/29/11.8 | #11 steel | 2019-05-29 | 2019-06-26 | 28 | D
5/29/11.9 | Exhaust fans | 2019-05-29 | 2019-06-19 | 21 | ALL
5/29/10.5 | Fire alarm pull station location | 2019-05-29 | 2019-06-12 | 14 | ALL
5/29/7.46 | Kiva duct penetrations | 2019-05-29 | 2019-06-19 | 21 | ALL
5/29/13.5 | Post bids | 2019-05-29 | 2019-06-26 | 28 | O
6/05/2.12 | Extra for water softener | 2019-06-05 | 2019-06-20 | 15 | O
6/05/5.14 | Shaft wall on first floor | 2019-06-05 | 2019-06-07 | 2 | ALL
6/05/7.47 | Black receptacles C211 | 2019-06-05 | 2019-06-07 | 2 | ALL
6/05/7.48 | Demo duct C107 | 2019-06-05 | 2019-06-13 | 8 | GC
6/05/7.49 | Dove gray sample louver | 2019-06-05 | 2019-06-19 | 14 | GC
6/05/7.50 | cores in floor for plumbing penetrations | 2019-06-05 | 2019-06-13 | 8 | D
6/05/7.51 | First floor classrooms | 2019-06-05 | 2019-06-07 | 2 | GC
6/05/7.52 | Standards for roof protection not followed | 2019-06-05 | 2019-06-06 | 1 | Gc
6/12/8.21 | Coring for fire panel | 2019-06-12 | 2019-06-25 | 13 | GC
6/12/6.11 | Bulletin #9 | 2019-06-12 | 2019-06-13 | 1 | GC
6/12/6.12 | Bulletin #10 | 2019-06-12 | 2019-06-13 | 1 | GC
6/12/7.53 | Walls between classroom/computer lab | 2019-06-12 | 2019-07-07 | 25 | D
6/12/7.54 | ASI be issued to document new fire panel | 2019-06-12 | 2019-07-07 | 25 | O
6/12/7.55 | fixing core that went through rebar | 2019-06-12 | 2019-06-13 | 1 | ALL
6/12/7.56 | occupany sensor layout drawing | 2019-06-12 | 2019-06-13 | 1 | D | Productivity for Owner for month of May= (No. of resolved issues/ Total No. of issues)x100
6/19/4.17 | Fire protection mounting | 2019-06-19 | 2019-06-20 | 1 | O
6/19/4.18 | AV Closet 106C | 2019-06-19 | 2019-06-20 | 1 | GC | Average Days to resolve issues for Owner = (No. of resolved issuesxNo. Of days for resolved issues)/ Total number of issues.
6/26/8.22 | fire suppression and devices operating | 2019-06-26 | 2019-07-23 | 27 | GC
6/26/8.23 | lobby work concern bulletin 10 | 2019-06-26 | 2019-08-16 | 51 | GC
6/26/5.15 | 8 open RFI | 2019-06-26 | 2019-07-21 | 25 | D
6/26/11.10 | Lighting controls resubmitted | 2019-06-26 | 2019-06-27 | 1 | ALL
6/26/6.13 | Bulletin #11 | 2019-06-26 | 2019-06-27 | 1 | GC
6/26/7.57 | Construction Issues #612, #594, #615 | 2019-06-26 | 2019-06-27 | 1 | GC | •WIP = (Number of Resolved Issues/ Total no. of issues)x total information exchange.
7/03/7.58 | General site issues | 2019-07-03 | 2019-07-30 | 27 | O | DV= (Information at Date X- Information at Date Y)/ Days in between
7/03/7.59 | Request into PBA exhaust fan curb | 2019-07-03 | 2019-07-30 | 27 | GC
7/03/7.60 | Close down birch road | 2019-07-03 | 2019-07-30 | 27 | O
7/10/2.13 | Steel stair and wall repair | 2019-07-10 | 2019-09-01 | 53 | ALL
7/10/8.24 | Shaft walls Bulletin 11 | 2019-07-10 | 2019-08-18 | 39 | ALL
7/10/11.11 | Fume Hood | 2019-07-10 | 2019-08-04 | 25 | O
7/10/11.12 | Exhaust fan motor | 2019-07-10 | 2019-08-18 | 39 | ALL
7/10/11.13 | Control Submittals | 2019-07-10 | 2019-09-01 | 53 | O
7/10/7.61 | Lobby ceilings color | 2019-07-10 | 2019-08-06 | 27 | O
7/10/7.62 | Power shut down | 2019-07-10 | 2019-07-11 | 1 | O
7/10/7.63 | Fin Tube | 2019-07-10 | 2019-07-11 | 1 | D
7/10/7.64 | Commissioning | 2019-07-10 | 2019-07-23 | 13 | GC
7/17/8.25 | Dorms floor 2-6 completing FA | 2019-07-17 | 2019-08-11 | 25 | GC
7/17/5.16 | Open RFIs 149,148,147,146,143 | 2019-07-17 | 2019-07-30 | 13 | D
7/17/6.14 | Bulletin #12 | 2019-07-17 | 2019-07-18 | 1 | GC
7/24/1.20 | Near miss incident report | 2019-07-24 | 2019-07-31 | 7 | GC
7/24/8.26 | Punch list for dorm | 2019-07-24 | 2019-07-25 | 1 | D
7/24/8.27 | Kiva corridor safe pathway | 2019-07-24 | 2019-07-25 | 1 | GC
7/24/4.19 | Bulletin #13 | 2019-07-24 | 2019-08-06 | 13 | D
7/24/10.6 | Fire marshal inspection | 2019-07-24 | 2019-08-06 | 13 | GC
7/24/6.15 | Bulletin #13 | 2019-07-24 | 2019-07-25 | 1 | GC
7/31/8.28 | Test and inspections | 2019-07-31 | 2019-08-01 | 1 | GC
7/31/8.29 | Crane pick | 2019-07-31 | 2019-08-01 | 1 | GC
7/31/7.65 | Steam Valve in Penthouse | 2019-07-31 | 2019-08-01 | 1 | GC
8/07/8.30 | Temp CO issued | 2019-08-07 | 2019-08-21 | 14 | GC
8/07/7.66 | Commissioning Items | 2019-08-07 | 2019-09-02 | 26 | GC
8/14/8.31 | Stud framing second floor | 2019-08-14 | 2019-08-27 | 13 | GC
8/14/8.32 | drywall first floor | 2019-08-14 | 2019-08-15 | 1 | GC
8/14/5.17 | 215 Air Line Locations | 2019-08-14 | 2019-08-15 | 1 | D
8/14/5.18 | 223 Door HW for existing | 2019-08-14 | 2019-08-15 | 1 | D
8/14/11.14 | Samples received | 2019-08-14 | 2019-08-28 | 14 | D
8/14/11.15 | Lab controls | 2019-08-14 | 2019-08-28 | 14 | D
8/14/7.67 | Crane Pick hoisting exhaust fans | 2019-08-14 | 2019-08-28 | 14 | GC
8/14/7.68 | Fire suppression bell | 2019-08-14 | 2019-09-10 | 27 | O
8/14/7.69 | Team Meeting | 2019-08-14 | 2019-09-03 | 20 | ALL
8/14/7.70 | Basement Column | 2019-08-14 | 2019-08-27 | 13 | GC
8/14/7.71 | Exterior Stair interference | 2019-08-14 | 2019-09-03 | 20 | O
8/14/7.72 | Bathroom items,dock entrance, signage | 2019-08-14 | 2019-09-10 | 27 | ALL
8/14/7.73 | Mens/Womens Lockers | 2019-08-14 | 2019-08-28 | 14 | GC
8/21/8.33 | MEP rough in | 2019-08-21 | 2019-08-22 | 1 | GC
8/21/8.34 | Core project schedule | 2019-08-21 | 2019-08-22 | 1 | GC
8/21/11.15 | 064023 Interior Architectural | 2019-08-21 | 2019-08-28 | 7 | D
8/21/5.19 | 225 LPC Height | 2019-08-21 | 2019-09-03 | 13 | D
8/21/5.20 | 227 Steel Railing | 2019-08-21 | 2019-08-28 | 7 | GC
8/21/11.16 | 271400 Communications Shop Drawings | 2019-08-21 | 2019-08-22 | 1 | D
8/21/11.17 | 096519 Resilient Tile Flooring | 2019-08-21 | 2019-08-22 | 1 | D
8/21/7.74 | Womens Room Lintel | 2019-08-21 | 2019-09-04 | 14 | D
8/21/7.75 | Art Work | 2019-08-21 | 2019-09-04 | 14 | ALL
9/4/5.21 | 227 Rockford to send steel information | 2019-09-04 | 2019-09-11 | 7 | GC
9/4/5.22 | 229 Screen heigh - TMP to return | 2019-09-04 | 2019-09-11 | 7 | D
9/4/11.18 | 115213 Projection Screen | 2019-09-04 | 2019-09-18 | 14 | D
9/4/7.76 | White boards to be put up by Rockford | 2019-09-04 | 2019-09-18 | 14 | GC
9/11/5.23 | 230 Paint first floor storage | 2019-09-11 | 2019-09-12 | 1 | O
9/11/5.24 | 231 Mechanical Room MEP Removal | 2019-09-11 | 2019-09-12 | 1 | D
9/11/5.25 | 232 Projector screen size | 2019-09-11 | 2019-09-12 | 1 | D
9/11/11.18a | 115213-1 Projection Screens | 2019-09-11 | 2019-09-18 | 7 | D
9/11/11.20 | 064023-3 Millwork Shop Drawings | 2019-09-11 | 2019-09-18 | 7 | D
9/11/11.21 | 102800-1 Bathroom Accessories | 2019-09-11 | 2019-09-12 | 1 | O
9/11/6.16 | Unifier | 2019-09-11 | 2019-09-12 | 1 | GC
9/11/7.77 | Stair versus ladder in penthouse | 2019-09-11 | 2019-09-19 | 8 | D
9/11/7.78 | Fire Alarm Punchlist | 2019-09-11 | 2019-09-13 | 2 | O
9/11/7.79 | Access Boxes | 2019-09-11 | 2019-09-13 | 2 | D
9/11/7.80 | Break Out Rooms | 2019-09-11 | 2019-09-25 | 14 | D
9/11/7.81 | Area 3 | 2019-09-11 | 2019-09-25 | 14 | D
9/11/7.82 | Poke Through Boxes | 2019-09-11 | 2019-09-13 | 2 | D
9/18/1.21 | Near miss incident drywall falling of lift | 2019-09-18 | 2019-09-20 | 2 | GC
9/18/5.26 | 234 Access panel size | 2019-09-18 | 2019-09-20 | 2 | D
9/18/5.27 | 236 Control Panel Placement | 2019-09-18 | 2019-09-20 | 2 | D
9/18/5.28 | 237 Sink Removal | 2019-09-18 | 2019-10-03 | 15 | O
9/18/11.22 | 288233-1 Convectors | 2019-09-18 | 2019-09-21 | 3 | D
9/18/7.83 | Mechanical Room Concrete Wall | 2019-09-18 | 2019-10-04 | 16 | O
9/18/7.84 | Projector Mounts | 2019-09-18 | 2019-10-04 | 16 | O
9/18/7.85 | Duct Transitions | 2019-09-18 | 2019-09-27 | 9 | ALL
9/25/5.29 | 248 General use air supply | 2019-09-25 | 2019-10-04 | 9 | D
9/25/5.30 | 250 Conduit for exterior lights | 2019-09-25 | 2019-10-11 | 16 | GC
9/25/5.31 | 251 Steam piping to unit heaters in penthouse | 2019-09-25 | 2019-10-11 | 16 | D
9/25/11.23 | 055213 - Railings | 2019-09-25 | 2019-09-28 | 3 | D
9/25/11.24 | 230923 - DDC HVAC Controls | 2019-09-25 | 2019-09-28 | 3 | D
9/25/6.17 | Bulletin #14 | 2019-09-25 | 2019-09-28 | 3 | GC
9/25/7.86 | North Entrance at Stair | 2019-09-25 | 2019-10-04 | 9 | ALL
9/25/7.87 | Insulation in mechanical room | 2019-09-25 | 2019-10-04 | 9 | GC
9/25/7.88 | Plate cover colors | 2019-09-25 | 2019-09-28 | 3 | D
10/2/4.20 | Update drawings for Don Mintz items | 2019-10-02 | 2019-10-05 | 3 | D
10/2/4.21 | Update drawings show Card Reader on engineering doors | 2019-10-02 | 2019-10-12 | 10 | D
10/2/5.32 | 255 West side tool lab wall | 2019-10-02 | 2019-10-06 | 4 | D
10/2/5.33 | 257 Misc lighting circuits switch | 2019-10-02 | 2019-10-06 | 4 | D
10/2/11.25 | 233713 Grills Registers Diffusers | 2019-10-02 | 2019-10-18 | 16 | D
10/2/11.26 | 093000 Tiling product data | 2019-10-02 | 2019-10-18 | 16 | D
10/2/6.18 | Bulletin #15 | 2019-10-02 | 2019-10-06 | 4 | GC
10/9/5.34 | 268 Cord Steel Height | 2019-10-09 | 2019-10-13 | 4 | D
10/9/5.35 | 265 Ceiling Steel | 2019-10-09 | 2019-10-13 | 4 | D
10/9/8.35 | 1st Floor Ceiling Grid | 2019-10-09 | 2019-10-13 | 4 | GC
10/9/8.36 | Basement wall repair underway | 2019-10-09 | 2019-10-26 | 17 | GC
10/9/8.37 | 2nd floor drywall hanging and finishing | 2019-10-09 | 2019-10-13 | 4 | GC
10/9/7.89 | MSU wants flood test in bathrooms | 2019-10-09 | 2019-10-13 | 4 | O
10/9/7.92 | Accelerated IT room schedule | 2019-10-09 | 2019-10-19 | 10 | GC
10/9/7.93 | Commissioning | 2019-10-09 | 2019-10-19 | 10 | GC
10/9/7.94 | Kiva technology added electronics | 2019-10-09 | 2019-10-13 | 4 | GC
10/9/7.95 | Epoxy flooring sample resubmission | 2019-10-09 | 2019-10-13 | 4 | GC/D
10/9/7.96 | Existing office space to be cleaned up | 2019-10-09 | 2019-10-20 | 11 | GC
10/9/7.97 | Steam pile tie in to start 10/16 | 2019-10-09 | 2019-10-14 | 5 | GC
10/16/6.19 | Bulletin 16 and 17 | 2019-10-16 | 2019-10-21 | 5 | GC
10/16/11.27 | 064023 Millwork Shop Drawings | 2019-10-16 | 2019-11-02 | 17 | D
10/16/5.36 | 269 Don Mintz electrical add | 2019-10-16 | 2019-11-02 | 17 | D
10/16/5.37 | 270 Flexible duct connection | 2019-10-16 | 2019-10-21 | 5 | D
10/16/5.38 | 271 duct insulation requirement | 2019-10-16 | 2019-10-21 | 5 | D
10/16/8.38 | Penthouse piping ongoing | 2019-10-16 | 2019-10-21 | 5 | GC
10/16/8.39 | Ductwork nearing completion | 2019-10-16 | 2019-10-21 | 5 | GC
10/23/8.40 | Floor finishes in first floor classrooms | 2019-10-23 | 2019-11-10 | 18 | GC
10/23/5.38 | 277 Feeder Pipes | 2019-10-23 | 2019-10-29 | 6 | D
10/23/5.39 | 263 Control Wiring | 2019-10-23 | 2019-11-11 | 19 | D
10/23/5.40 | 261 VFD Location | 2019-10-23 | 2019-11-11 | 19 | D
10/23/7.98 | AV Meeting | 2019-10-23 | 2019-11-04 | 12 | GC
10/23/7.99 | Base in 1st Floor | 2019-10-23 | 2019-11-04 | 12 | GC
10/30/8.41 | Kiva ready for flooring delivery | 2019-10-30 | 2019-11-18 | 19 | GC
10/30/8.42 | Furniture delivery scheduled for Dec. 6 | 2019-10-30 | 2019-11-18 | 19 | GC
10/30/5.41 | 278 Pipe Grid | 2019-10-30 | 2019-11-05 | 6 | D
10/30/5.42 | 279 Duct detector removal | 2019-10-30 | 2019-11-05 | 6 | D
10/30/5.43 | 280 Lighting layout | 2019-10-30 | 2019-11-02 | 3 | D
10/30/11.28 | 33000 Cast In Place Concrete | 2019-10-30 | 2019-11-15 | 16 | GC
10/30/6.20 | Bulletin 18 | 2019-10-30 | 2019-11-15 | 16 | GC
10/30/6.21 | Bulletin 19 | 2019-10-30 | 2019-11-08 | 9 | GC
11/6/6.22 | Bulletin 20 | 2019-11-06 | 2019-11-15 | 9 | GC
11/6/5.44 | 284 Lighting conflict with duct | 2019-11-06 | 2019-11-22 | 16 | D
11/6/5.45 | 285 exit lights | 2019-11-06 | 2019-11-22 | 16 | D
11/6/5.46 | 286 L7 lights in C213 | 2019-11-06 | 2019-11-09 | 3 | D
11/6/5.47 | 287 Conduit for AV | 2019-11-06 | 2019-11-09 | 3 | D
11/6/7.100 | Electrical shutdown | 2019-11-06 | 2019-11-09 | 3 | GC
11/6/7.101 | Duct detectors | 2019-11-06 | 2019-11-15 | 9 | D
11/6/7.102 | Elevator finishes | 2019-11-06 | 2019-11-15 | 9 | GC
11/6/7.103 | Acoustic sound panels | 2019-11-06 | 2019-11-09 | 3 | GC
57.1
Formulas:
End Date = [Start Date]+[Days to Complete]
Start Date = [Start Date, row above]
Note on F8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Randy Evans (unknown) Matt Postma (MSU) Terry Cleis (PBA)
Note on B13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mentioned in cell C21
Note on E14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: double check dates
Note on B28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Bulletin #2 mentioned in cell C13
Note on A39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Arbitrary transition from GC to O (no details given)
Note on F55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: "Matt" listed as responsible, which matt?
Note on F68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: douglas steel providing price per Designer standard
Note on M141: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: format of submittals changed 8/21 - now assigned numbers to each line item
Note on B218: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mentioned in Cell C212
Note on B227: Alexis Ly: separating the RFIs into different line items since the format changed in the meeting minutes starting 8/14
Note on B255: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: format of submittals changed 8/21 - now assigned numbers to each line item

## Types of Issues
Recirpocal | Pooled | Intensive | Sequential
cafeteria demo | water leak | fire alarm | Plan grid training
elevator | Bulletin #1 | 3 bid RFI's | PBA admin for plan grid
bids due | lighting controls | Bulletin #2 | award recommendations
post bid meeting schedule | Bulletin #1 | kitchen abatement | award recommendations
addendum #1 | Unifier | Incident Report - fence collapse | award recommendations
project schedule concern | Unifier | basement demo/abatment | abatment training
basement demo/abatment | Unifier | basement demo/abatment | abatment training
furniture budget | TMP to issue Bulletin #2 | Quarry tile | abatment training
student room flooring | MSU leadership presentation | Quarry tile | Crane swing concern, plan to set crane, tree damage waiver
install standpipes in dorm wign | electrician needs permit | Quarry tile | occupany sensor layout drawing
student suite mock up | hot water piping approval | KIVA flooring | AV Closet 106C
potentially ahead of schedule | Kiva Lighting | fire suppression core | Construction Issues #612, #594, #615
glazed block demo | Alt #3 VE idea | steel/drywall/fire suppression/plumbing approval | General site issues
pipe insulation demo request | Alt #3 VE idea | 2 week look ahead | Request into PBA exhaust fan curb
completion schedule | Alt #3 VE idea | plans submitted to fire/Safety office | Close down birch road
GC cost summary review | Alt #3 VE idea | Campus art locations | Fume Hood
acoustical baffles | hot water piping replacement | fire suppression mock up | Lobby ceilings color
2nd floor demo | Bulletin #2 pricing | dorm flooring abatement | Power shut down
bay loading concerns | Replaced damaged light | fire alarm knocked out | Fin Tube
budget update | KIVA lighting | fire alarm demo | Commissioning
gypcrete | Guy (MSU) to review light fixture submittal | fire alarm demo | Dorms floor 2-6 completing FA
floor loading on 2nd floor | Bulletin #3 issued | fire alarm demo | Near miss incident report
pro-press substitute | Bulletin #4 | subs must wear PPE | Punch list for dorm
master submittal log | Bulletin #5, cable tray elec floor box | additional basement samples | Kiva corridor safe pathway
AV bid | ADA ramp letter to MSU legal | basement shop demo | Test and inspections
ADA budget | TMP alternate guardrail for rooftop HVAC | low density fill - 2nd floor | Crane pick
ADA budget | hot water shutoff 6:00AM | existing basement conduit support | Steam Valve in Penthouse
ADA budget | Bulletin #6 | digital screen mounts | Temp CO issued
ADA budget | Room C211A IT changes, ceiling, light, paint, walls | MEP | Commissioning Items
price added angle iron for roof | Water shutoff notice | ASI #1 | Stud framing second floor
demo & additional work | MSU remove furniture piano projectors KIVA | no work during final exams | drywall first floor
6th floor - ceiling asbestos | Bulletin #7 | Art on Campus Meeting | Samples received
Englarged glass area | when water will be turned back on | Existing gas line turned off | Lab controls
CAD drawings | Bulletin to capture AV changes | TMP to provide specific floor box location | Crane Pick hoisting exhaust fans
2nd floor metal framing | Water shutoff entire building duration | TMP to provide saw cut layout | Team Meeting
sprinkler head cages | Extra for water softener | RFI #95 access to install plumbing | Basement Column
FADE | Bulletin #9 | Future submittals go to Matt P to forward to TMP | Exterior Stair interference
FADE | Bulletin #10 | Expoxy floor color finalize hold up | Bathroom items,dock entrance, signage
FADE | Lighting controls resubmitted | request to demo existing fire suppression system to second floor pipe penetrations | Mens/Womens Lockers
FADE | Bulletin #11 | requested access to dorm area for core layout | MEP rough in
AV design | Bulletin #12 | wall taken down new pump room first floor | 271400 Communications Shop Drawings
cold formed metal framing | Bulletin #13 | steel delivery coordination, road closure | Womens Room Lintel
shop questions/review | Bulletin #13 | Ball valves approved | Art Work
WIFI | Unifier | existing abandoned gas pipe basement removed | White boards to be put up by Rockford
items currently purchased | Access Boxes | #96,97,98,99,101 steel RFI expedite | Stair versus ladder in penthouse
items to be included in scope | Break Out Rooms | RFI #93
Generate bid package | Area 3 | Additional ceiling removal room 41
Dates | Poke Through Boxes | Existing fin tube
asbestos awareness | Near miss incident drywall falling of lift | how many IGDs included fire system
wall layout | 288233-1 Convectors | Steam shutdown
cold form metal framing - box beam | Mechanical Room Concrete Wall | All dorm rooms unlocked 5:00AM
#76 compactor room ceiling demo | Projector Mounts | Basement fire suppression piping above ceiling
#57 classroom ceiling height @ bulkhead | Duct Transitions | A6.2 & A12.2 furniture plan
H&R has permit | 248 General use air supply | no external content placed on IGDs
furniture meeting | 250 Conduit for exterior lights | A/V, Epoxy floor, overhead doors
1st floor ceiling duct penetration | 251 Steam piping to unit heaters in penthouse | A/V, Epoxy floor, overhead doors
Master campus schedule for summer | Bulletin #14 | first room fire alarm conduit mockup
Finals week classroom schedule | North Entrance at Stair | Need access to rooms 11,26,28
Write up and budget convert C202C computer lab | Insulation in mechanical room | Cable tray spec
review cost summary log | Plate cover colors | Piping penetration sleeves
#11 steel | Update drawings for Don Mintz items | Painting fire alarm fire suppression risers
215 Air Line Locations | Update drawings show Card Reader on engineering doors | RFI #119
223 Door HW for existing | 255 West side tool lab wall | LaForce Total Door and LCN closers
Core project schedule | 257 Misc lighting circuits switch | review safety and freq of GC safety inspection
064023 Interior Architectural | Bulletin #15 | upload GC and trade site safety program, tool box talk, safety report
225 LPC Height | 268 Cord Steel Height | 6th floor fire suppression shop drawings
227 Steel Railing | 265 Ceiling Steel | pricing for supporting existing basement conduit
096519 Resilient Tile Flooring | Basement wall repair underway | Floor variance C211, C213, C215
227 Rockford to send steel information | 2nd floor drywall hanging and finishing | elevator room abatement
229 Screen heigh - TMP to return | MSU wants flood test in bathrooms | review fire alarm conduit layout in South lobby
115213 Projection Screen | Commissioning | potential change to penthouse access
230 Paint first floor storage | Kiva technology added electronics | South dorm wing coring concrete beam
231 Mechanical Room MEP Removal | Epoxy flooring sample resubmission | RFI requesting to lower D hallway ceiling
232 Projector screen size | Existing office space to be cleaned up | Review fire panel location lobbies
115213-1 Projection Screens | Steam pile tie in to start 10/16 | Wonder bodies equipment removed
064023-3 Millwork Shop Drawings | Bulletin 16 and 17 | Central core south stair ceiling removed steel install
102800-1 Bathroom Accessories | 269 Don Mintz electrical add | Two approved roofers backed out
234 Access panel size | 270 Flexible duct connection | Steel Shop and RFI roof curb
236 Control Panel Placement | 271 duct insulation requirement | Fire panel locations
237 Sink Removal | Penthouse piping ongoing | Intermediate offices
055213 - Railings | Ductwork nearing completion | Exhaust fans
230923 - DDC HVAC Controls | Floor finishes in first floor classrooms | Fire alarm pull station location
233713 Grills Registers Diffusers | 277 Feeder Pipes | Kiva duct penetrations
093000 Tiling product data | 263 Control Wiring | Post bids
1st Floor Ceiling Grid | 261 VFD Location | Shaft wall on first floor
Accelerated IT room schedule | AV Meeting | Black receptacles C211
064023 Millwork Shop Drawings | Base in 1st Floor | Demo duct C107
Furniture delivery scheduled for Dec. 6 | Kiva ready for flooring delivery | Dove gray sample louver
| 278 Pipe Grid | cores in floor for plumbing penetrations
| 279 Duct detector removal | First floor classrooms
| 280 Lighting layout | Standards for roof protection not followed
| 33000 Cast In Place Concrete | Coring for fire panel
| Bulletin 18 | Walls between classroom/computer lab
| Bulletin 19 | ASI be issued to document new fire panel
| Bulletin 20 | fixing core that went through rebar
| 284 Lighting conflict with duct | Fire protection mounting
| 285 exit lights | fire suppression and devices operating
| 286 L7 lights in C213 | lobby work concern bulletin 10
| 287 Conduit for AV | 8 open RFI
| Electrical shutdown | Steel stair and wall repair
| Duct detectors | Shaft walls Bulletin 11
| Elevator finishes | Exhaust fan motor
| Acoustic sound panels | Control Submittals
Open RFIs 149,148,147,146,143
Fire marshal inspection
Fire suppression bell
Fire Alarm Punchlist
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mentioned in cell C21
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Bulletin #2 mentioned in cell C13
Note on A66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: format of submittals changed 8/21 - now assigned numbers to each line item
Note on C102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mentioned in Cell C212
Note on C105: Alexis Ly: separating the RFIs into different line items since the format changed in the meeting minutes starting 8/14

## Sheet3
Meeting Date | Emails to D | Email to O | Email to GC | PlanGrid | Unifier | Issues to D | Issues to O | Issues to GC
2019-01-23 | 73 | 11 | 7 | 0 | 19 | 10 | 7 | 5
2019-02-11 | 107 | 32 | 17 | 5 | 32 | 13 | 6 | 4
2019-02-20 | 38 | 7 | 2 | 0 | 24 | 19 | 10 | 4
2019-02-27 | 33 | 11 | 3 | 2 | 10 | 26 | 8 | 8
2019-03-06 | 48 | 9 | 0 | 22 | 0 | 30 | 11 | 10
2019-03-13 | 38 | 10 | 5 | 10 | 0 | 32 | 12 | 8
2019-03-20 | 3 | 1 | 2 | 34 | 36 | 44 | 13 | 7
2019-03-27 | 37 | 65 | 12 | 0 | 44 | 43 | 16 | 3
2019-04-03 | 103 | 74 | 17 | 0 | 17 | 36 | 20 | 3
2019-04-10 | 71 | 88 | 5 | 9 | 48 | 26 | 23 | 4
2019-04-17 | 85 | 62 | 1 | 0 | 1 | 21 | 22 | 4
2019-04-24 | 74 | 83 | 14 | 0 | 67 | 27 | 11 | 8
2019-05-08 | 68 | 119 | 35 | 0 | 9 | 23 | 10 | 10
2019-05-15 | 54 | 89 | 35 | 108 | 38 | 25 | 12 | 5
2019-05-22 | 49 | 87 | 24 | 0 | 22 | 31 | 12 | 5
2019-05-29 | 86 | 86 | 52 | 0 | 29 | 31 | 6 | 5
2019-06-05 | 32 | 50 | 13 | 82 | 37 | 26 | 6 | 5
2019-06-12 | 67 | 129 | 29 | 0 | 28 | 18 | 9 | 4
2019-06-19 | 50 | 58 | 30 | 0 | 2 | 4 | 3 | 4
2019-06-26 | 65 | 79 | 43 | 118 | 5 | 3 | 5 | 14
2019-07-03 | 59 | 141 | 42 | 0 | 23 | 3 | 5 | 20
2019-07-10 | 53 | 62 | 61 | 0 | 11 | 3 | 3 | 22
2019-07-17 | 65 | 86 | 77 | 66 | 15 | 5 | 3 | 23
2019-07-24 | 39 | 93 | 27 | 42 | 13 | 2 | 3 | 22
2019-07-31 | 74 | 98 | 34 | 13 | 29 | 3 | 3 | 20
2019-08-07 | 32 | 84 | 31 | 0 | 15 | 2 | 3 | 19
2019-08-14 | 133 | 300 | 76 | 94 | 49 | 3 | 0 | 14
2019-08-21 | 56 | 131 | 33 | 6 | 35 | 1 | 0 | 12
2019-09-04 | 19 | 110 | 25 | 17 | 21 | 2 |  | 13
2019-09-11 | 43 | 90 | 13 | 16 | 24 | 1 |  | 11
2019-09-18 | 22 | 58 | 11 | 16 | 23 |  |  | 9
2019-09-25 | 38 | 127 | 19 | 13 | 52 |  |  | 10
2019-10-02 | 36 | 109 | 33 | 18 | 48 |  | 1 | 14
2019-10-09 | 32 | 117 | 52 | 45 | 15 | 1 | 1 | 13
2019-10-16 | 29 | 93 | 49 | 43 | 34 | 1 |  | 15
2019-10-23 | 25 | 151 | 70 | 45 | 44 |  |  | 18
2019-10-30 | 24 | 137 | 49 | 49 | 49 |  | 1 | 14
2019-11-06 | 19 | 111 | 55 | 53 | 37 |  | 1 | 19